# Project Plan – Marketing Mix Modelling

Course: Project Algorithms 3722PRALGA

Client: Group M

Date: 20 April 2025

——————————————————————————————

## Group Members

- Nikita Marfitsyn (711189)

- Baraa Semsmieh (656645)

- Mehedi Hasan  (712553)

- Joost Donders (687268)

- Ayitey  Nii-Armah (714025)

——————————————————————————————

## Table of Contents

1. Introduction

2. Context

2.1 Preliminary Research Results

2.2 Situation in the Organization

2.3 Problem Statement

3. Goal of the Project

3.1 Objectives

3.2 Research Questions

4. Preconditions

5. Methodology

6. Risks and Solutions

6.1 External Risks

6.2 Internal Risks

7. Task Division and Planning

7.1 Product Breakdown

7.2 Work Breakdown

7.3 Task Distribution

8. Contact Information

——————————————————————————————

## 1. Introduction

This document outlines the initial project plan for our assignment on Marketing Mix Modelling (MMM). The purpose is to deliver a predictive model that quantifies the effectiveness of media spending and guides future budget allocation. Since we have not had contact with the client yet, many details remain undefined. This plan represents our best assumptions based on the course guide and provided challenge description.

——————————————————————————————

## 2. Context

- 2.1 Preliminary Research Results

Marketing Mix Modelling (MMM) is a technique used to quantify the impact of various marketing channels on sales. It leverages historical sales and media spend data to create statistical models that forecast sales and optimize future media investment.

- 2.2 Situation in the Organization

Group M is the world’s leading media-investment group. They provide services aimed at optimizing advertising impact through data and innovation. Our task is to assist in this mission by modelling their data effectively.

- 2.3 Problem Statement

The Clients need to know how to allocate their media budgets to maximize return on investment. The problem is to predict the effect of different marketing channels on sales and suggest an optimal media budget distribution.

——————————————————————————————

## 3. Goal of the Project

- 3.1 Objectives

- Build a predictive model linking marketing spend to sales.

- Analyze the effectiveness of different media channels.

- Provide actionable insights for future budgeting.

- 3.2 Research Questions

- Main Question:

How can we model the relationship between marketing spend and sales to improve budget allocation?

- Sub-questions:

- Which media channels have the most impact on sales?

- What is the ROI per channel?

- How can we forecast sales under various budget scenarios?

- What limitations exist in the dataset, and how can they be mitigated?

- Can external data improve the model’s accuracy?

——————————————————————————————

## 4. Preconditions

At the moment, we have not yet received the dataset from Group M, nor have we had contact with the client. Thus, we are unable to confirm:

- Data completeness or structure.

- Whether external factors (seasonality, economic indicators, etc.) will be available or relevant.

- Client expectations regarding technical delivery and format.

These factors will be clarified once communication with the client begins.

——————————————————————————————

## 5. Methodology

We will explore different modelling techniques, such as:

- Linear regression and regularized models (Ridge, Lasso).

- Time series analysis or machine learning models depending on data granularity.

- Feature engineering to account for lag effects, seasonality, and diminishing returns.

Our approach will evolve as we explore the dataset and understand its limitations.

——————————————————————————————

## 6. Risks and Solutions

- 6.1 External Risks:

| Risk | Chance | Impact | Priority | Mitigation |
| --- | --- | --- | --- | --- |
| Lack of contact with client | 5 | 5 | 25 | Follow up via course tutor if contact is not initiated soon. |
| Dataset is incomplete or noisy | 4 | 5 | 20 | Identify gaps early, propose solutions (e.g., find external data). |
| Misunderstanding client goals | 4 | 4 | 16 | Ask clarifying questions during first meeting. |

- 6.2 Internal Risks:

| Risk | Chance | Impact | Priority | Mitigation |
| --- | --- | --- | --- | --- |
| No clear division of roles | 5 | 4 | 20 | Assign roles tentatively, adjust post-client meeting. |
| Limited experience with MMM | 3 | 4 | 12 | Research academic and industry MMM practices, consult tutor. |
| Low quality of communication within the team | 5 | 5 | 25 | Set clear communication norms and regular updates; hold each other accountable. |

——————————————————————————————

## 7. Task Division and Planning

- 7.1 Product Breakdown

The product consists of:

- A functional model.

- A presentation and report explaining results.

- Supporting documentation.

- 7.2 Work Breakdown

Given that roles are not fixed and client expectations are unknown, here is a tentative plan:

- Week 1–2: Research MMM and similar projects; study relevant algorithms and models.

- Week 2–3: First draft of model using placeholder or sample data.

- Week 3–5: Refine model once we have real data and clearer goals.

- Week 6–7: Prepare deliverables (report, slides, documentation).

- Week 8: Final presentation and submission.

- 7.3 Task Distribution

We haven’t finalized task distribution yet because we need to talk to the client to understand what is needed. Additionally, we have not formally assigned roles yet, but we are loosely split between those more experienced with coding and those focused on modeling or research. These will be clarified as the project progresses.

——————————————————————————————

## 8. Contact Information

Nikita Marfitsyn - 711189@student.inholland.nl

Baraa Semsmieh - 656645@student.inholland.nl

Mehedi Hasan - 712553@student.inholland.nl

Joost Donders - 687268@student.inholland.nl

Ayitey Nii-Armah- 714025@student.inholland.nl